## Sheet1
Issue Name | Assignees | Labels | Projects | Milestones
Wireframe Creation | Designer | UI/UX, Design | Mobile App Prototype | UI/UX Design
Interactive Mock-ups | Designer | UI/UX, Prototype | Mobile App Prototype | UI/UX Design
Usability Testing Round 1 | QA Tester | Testing, Usability | Mobile App Prototype | UI/UX Design
Anonymous Reporting Flow | Developer | Core Feature, Reporting | Mobile App Prototype | Core Feature Build
Geolocation Tagging | Developer | Core Feature, GPS | Mobile App Prototype | Core Feature Build
Offline Mode Logic | Developer | Core Feature, Offline | Mobile App Prototype | Core Feature Build
Choose Cross-Platform Framework | Lead Developer | Architecture, Tech Stack | Technical Architecture Document | Tech Stack Definition
Backend Service Design | Developer | Architecture, Backend | Technical Architecture Document | Tech Stack Definition
Security & Encryption Plan | Developer | Architecture, Security | Technical Architecture Document | Tech Stack Definition
Entity-Relationship Modelling | Developer | Database, Design | Technical Architecture Document | Database & API Design
API Endpoint Planning | Developer | API, Backend | Technical Architecture Document | Database & API Design
Offline Data-Handling Schema | Developer | API, Offline | Technical Architecture Document | Database & API Design
Define 12 Monthly Goals | Project Manager | Planning, Goals | Monthly Milestone Plan | Project Planning
Create Gantt Chart/Agile Board | Project Manager | Planning, Agile | Monthly Milestone Plan | Project Planning
Schedule Review Meetings | Project Manager | Meetings, Planning | Monthly Milestone Plan | Project Planning
Monthly Report Templates | Project Manager | Reporting, Updates | Monthly Milestone Plan | Stakeholder Updates
Communication Workflow Setup | Project Manager | Communication | Monthly Milestone Plan | Stakeholder Updates
Presentation Material for Updates | Project Manager | Reporting, Presentations | Monthly Milestone Plan | Stakeholder Updates
Recruit Test Participants | QA Tester | Testing, Participants | User Testing & Feedback Report | Test Planning
Create Test Cases & Forms | QA Tester | Testing, Forms | User Testing & Feedback Report | Test Planning
Setup Testing Tools | QA Tester | Testing, Tools | User Testing & Feedback Report | Test Planning
Gather Usability Data | QA Tester | Feedback, Usability | User Testing & Feedback Report | Feedback Analysis
Categorise Issues | QA Tester | Feedback, Categorisation | User Testing & Feedback Report | Feedback Analysis
Compile Iteration Suggestions | Designer & Developer | Feedback, Improvement | User Testing & Feedback Report | Feedback Analysis
Code Final Features | Developer | Final Build, Features | Final Release & Deployment Package | Final Development & QA
Full Regression Testing | QA Tester | Final Build, Testing | Final Release & Deployment Package | Final Development & QA
Fix Priority Bugs | Developer | Final Build, Bugs | Final Release & Deployment Package | Final Development & QA
Store Submission | Developer | Deployment, Publishing | Final Release & Deployment Package | Deployment & Documentation
Prepare User Manual | Project Manager | Documentation | Final Release & Deployment Package | Deployment & Documentation
Training Video or Guide | Designer | Documentation, Training | Final Release & Deployment Package | Deployment & Documentation